## Sheet1
Project Name |  | : WM-EKSLUSIF
Project Leader |  | : Virya Yasa Santoso
Member |  | : Raisa Aqila Alfadzila, Amar Abdullah Sulammi
Start Date |  | 2024-05-31
End Date
Overall Progress |  | 100% |  |  |  |  | Keterangan : | Dilakukan | Revisi | Rencana
No | Tasks | PIC | Due Date | Status | Percentage | 01-Juni - 07-Juni | 08-Juni - 14-Juni | 15-Juni - 21-Juni | 22-Juni - 28-Juni | 29-Juni - 05-Juli | 06-Juli - 12-Juli | 13-Juli - 19-Juli | 20-Juli - 26-Juli | 27-Juli - 02-Agustus
1 | Penentuan Kelompok | Dosen & Instruktur | 2024-05-31 | Completed | 100%
2 | Penentuan Tema Project | Dosen & Instruktur | 2024-05-31 | Completed | 100%
3 | Penentuan Master | Kelompok | 2024-06-05 | Completed | 100%
4 | Penentuan Transaksi | Kelompok | 2024-06-05 | Completed | 100%
5 | Penentuan Laporan | Kelompok | 2024-06-05 | Completed | 100%
6 | ERD, PDM dan Flowchart | Kelompok | 2024-06-10 | Completed | 100%
7 | Penentuan Hak Akses | Kelompok | 2024-06-10 | Completed | 100%
8 | Penentuan Menu | Kelompok | 2024-06-10 | Completed | 100%
9 | Master 1 (Pelanggan)
A. | Create Master 1 | Virya | 2024-06-20 | Completed | 100%
B. | Read Master 1 | Virya | 2024-06-20 | Completed | 100%
C. | Update Master 1 | Virya | 2024-06-20 | Completed | 100%
D. | Delete Master 1 | Virya | 2024-06-20 | Completed | 100%
10 | Master 2 (Distributor)
A. | Create Master 2 | Raisa | 2024-06-20 | Completed | 100%
B. | Read Master 2 | Raisa | 2024-06-20 | Completed | 100%
C. | Update Master 2 | Raisa | 2024-06-20 | Completed | 100%
C. | Update Master 3 | Raisa | 2024-06-20 | Completed | 100%
D. | Delete Master 2 | Raisa | 2024-06-20 | Completed | 100%
11 | Master 3 (Produk)
A. | Create Master 3 | Raisa | 2024-06-20 | Completed | 100%
B. | Read Master 3 | Raisa | 2024-06-20 | Completed | 100%
C. | Update Master 3 | Raisa | 2024-06-20 | Completed | 100%
D. | Delete Master 3 | Raisa | 2024-06-20 | Completed | 100%
12 | Master 4 (Karyawan)
A. | Create Master 4 | Amar | 2024-06-20 | Completed | 100%
B. | Read Master 4 | Amar | 2024-06-20 | Completed | 100%
C. | Update Master 4 | Amar | 2024-06-20 | Completed | 100%
D. | Delete Master 4 | Amar | 2024-06-20 | Completed | 100%
13 | Master 5 (Promo/Diskon)
A. | Create Master 5 | Virya | 2024-06-20 | Completed | 100%
B. | Read Master 5 | Virya | 2024-06-20 | Completed | 100%
C. | Update Master 5 | Virya | 2024-06-20 | Completed | 100%
D. | Delete Master 5 | Virya | 2024-06-20 | Completed | 100%
14 | Master 6 (Jenis Member)
A. | Create Master 7 | Virya | 2024-06-20 | Completed | 100%
B. | Read Master 7 | Virya | 2024-06-20 | Completed | 100%
C. | Update Master 7 | Virya | 2024-06-20 | Completed | 100%
D. | Delete Master 7 | Virya | 2024-06-20 | Completed | 100%
15 | Master 7 (Kategori Jabatan)
A. | Create Master 7 | Amar | 2024-06-10 | Completed | 100%
B. | Read Master 7 | Amar | 2024-06-10 | Completed | 100%
C. | Update Master 7 | Amar | 2024-06-10 | Completed | 100%
D. | Delete Master 7 | Amar | 2024-06-10 | Completed | 100%
16 | Master 8 (Kategori Produk)
A. | Create Master 8 | Raisa | 2024-06-20 | Completed | 100%
B. | Read Master 8 | Raisa | 2024-06-20 | Completed | 100%
C. | Update Master 8 | Raisa | 2024-06-20 | Completed | 100%
D. | Delete Master 8 | Raisa | 2024-06-20 | Completed | 100%
17 | Penggabungan Master | Virya | 2024-06-25 | Completed | 100%
18 | Transaksi 1 (Penjualan)
A. | Create Transaksi 1 | Amar | 2024-07-05 | Completed | 100%
B. | Read Transaksi 1 | Amar | 2024-07-05 | Completed | 100%
19 | Transaksi 2 (Pembelian)
A. | Create Transaksi 2 | Virya, Raisa | 2024-07-05 | Completed | 100%
B. | Read Transaksi 2 | Virya, Raisa | 2024-07-05 | Completed | 100%
20 | Penggabungan Transaksi | Amar | 2024-07-06 | Completed | 100%
21 | Laporan 1 (Rekap Penjualan)
A. | Read Laporan 1 | Amar, Virya | 2024-07-07 | Completed | 100%
22 | Laporan 2 (Rekap Pembelian)
A. | Read Laporan 2 | Raisa, Virya | 2024-07-07 | Completed | 100%
23 | Penggabungan Laporan | Amar | 2024-07-08 | Completed | 100%
24 | Dashboard Admin | Raisa, Amar | 2024-07-11 | Completed | 100%
24 | Dashboard Cashier | Virya | 2024-07-12 | Completed | 100%
24 | Dashboard Manager | Virya, Amar | 2024-07-13 | Completed | 100%
25 | Sidang | Kelompok | 2024-07-16 | On Progress | 100%